ARRO Medical Specialist Task Card

Challenge details

| Challenge dates |  |
| --- | --- |
| Challenge location |  |
| Host agency |  |
| Host contact (name/number/email) |  |
| Venue name |  |
| Venue address |  |
| Venue contact (name/number/email) |  |

Challenge Management Team – Medical Assessor details

| Medical Assessor Mentor (name/number/email) |  |
| --- | --- |
| Time Critical Assessor (name/number/email) |  |
| Entrapped Assessor (name/number/email) |  |
| Controlled Assessor 1 (name/number/email) |  |

Challenge Management Team – Moulage Team details

| Moulage Specialist 1 (name/number/email) |  |
| --- | --- |
| Moulage Specialist 2 (name/number/email) |  |

Pre-challenge checklist for Medical Specialist (T-6 months)

| - Work alongside Resuscitation Officer to confirm availability of Medical Assessors |  |
| --- | --- |
| - Tentatively select Trauma / Medical Assessors with Resuscitation Officer |  |
| - Recommend Trauma / CPR / Medical Assessors to Technical Panel |  |
| - Recommend a medical theme for the Learning Symposium to the Technical Panel |  |
| - Recommend a medical theme for the Workshop to the Technical Panel (if applicable) |  |
| - Review/update/confirm Road Crash Rescue Rules/Objectives with Technical Committee |  |

Pre-challenge checklist for Medical Specialist (T-4 months)

| - Create a high-level plan for the Learning Symposium |  |
| --- | --- |
| - Create a high-level plan for the Workshop (if applicable) |  |
| - Update Resuscitation Officer and Technical Panel |  |

Pre-challenge checklist for Medical Specialist (T-3 months)

| - Send high-level plan for the Learning Symposium to the Technical Panel |  |
| --- | --- |
| - Contact the Host/Local Ambulance Authority if support is needed in the Symposium |  |
| - Send high-level plan for the Workshop to the Technical Panel |  |
| - Contact the Host/Local Ambulance Authority if support is needed in the Workshop |  |
| - Request two Laerdal QCPR Manikins from a Local Ambulance Authority or the supplier |  |

Pre-challenge checklist for Medical Specialist (T-2 months)

| - Participate in ‘check in’ teleconference with Trauma Coordinator & Moulage Specialist |  |
| --- | --- |
| - Confirm number of patients needed & pass this to Challenge Coordinator |  |
| - Confirm CPR Challenge Pit requirements and pass to Challenge Coordinator |  |
| - Participate in bi-weekly Technical Committee Teleconferences |  |
| - Touch base with Host Agency re support for Symposium/Workshop |  |
| - Touch base with Local Ambulance Authority re support for Symposium/Workshop |  |
| - Co-author update communication to Trauma/Medical Assessors |  |

Pre-challenge checklist for Medical Specialist (T-1 month)

| - Participate in ‘check in’ teleconference with Trauma Coordinator & Moulage Specialist |  |
| --- | --- |
| - Follow up on patient numbers and requirements with Challenge Coordinator |  |
| - Touch base with Host Agency to confirm support for Symposium/Workshop |  |
| - Touch base with Local Ambulance Authority to confirm support for Symposium/Workshop |  |
| - Touch base with supplier of the Laerdal QCPR Manikins |  |
| - Co-author update communication to Trauma/Medical Assessors with Trauma Coordinator |  |
| - Participate in bi-weekly Technical Committee Teleconferences |  |

Challenge checklist for Medical Specialist (prep-days)

| - Meet with Resuscitation Officer & Moulage Specialists |  |
| --- | --- |
| - Select the rescue scenarios with the Scenario Managers |  |
| - Update the medical sheets associated with the rescue scenarios |  |
| - Print medical sheets associated with rescue Scenarios (colour preferred, two of each) |  |
| - Place medical sheets into two folders in competition order – pass to Moulage Specialist |  |
| - Confirm Laerdal QCPR Manikin present & work with host agency to set up CPR Challenge |  |
| - Confirm all symposium/workshop resources are present |  |
| - Charge and check Medical Assessor headsets |  |

Challenge checklist for Medical Specialist (CMT Workshop)

| - Acknowledge all Medical/CPR/Trauma Assessors as they arrive |  |
| --- | --- |
| - Overview the medical aspect of the RCR Challenge, rules and objectives at CMT briefing |  |
| - Overview the CPR Challenge, rules and objectives at CMT briefing |  |
| - Co-facilitate the Medical Assessor briefing/discussion with the Resuscitation Officer |  |
| - Work with the Medical/Trauma Assessors to check/stock medical kits |  |
| - Work with the Medical/Trauma Assessors to check/stock medical spares |  |
| - Move all medical kits and spares to the pits |  |
| - Test the Laerdal QCPR Manikins in the CPR Challenge Pit |  |
| - Reconfirm all start times/rigs/rules of engagement with Medical/CPR/Trauma Assessors |  |
| - Confirm patients with Moulage Specialist/Challenge Coordinator/Volunteers Coordinator |  |

Symposium checklist for Medical Specialist (Learning Symposium)

| - Support any medical speakers as required |  |
| --- | --- |
| - Lead medical related stakeholder management |  |
| - Lead/coordinate the medical aspect of the learning symposium |  |
| - Ensure medically related workshop resources are present in the workshop pit |  |

Challenge checklist for Medical Specialist (during challenge)

| - Check in each morning with Moulage Specialists to ensure their requirements are met |  |
| --- | --- |
| - Check in each morning with Medical Assessors to ensure their requirements are met |  |
| - Check in each morning/evening with Resuscitation Officer |  |
| - Lead medical related stakeholder management |  |
| - Work with Trauma Coordinator to coordinate pack up of medical equipment/supplies |  |
| - Check and pack up Medical Assessor headsets |  |
| - Ensure all borrowed equipment is thoroughly cleaned and returned |  |

Post-challenge checklist for Medical Specialist (T+2 weeks)

| - Send thank you/acknowledgement email to Host Agency |  |
| --- | --- |
| - Send thank you/acknowledgement email to Local Ambulance Authority |  |
| - Co-author thank you email to Medical Assessors with Medical Specialist |  |
| - Thank any medical related stakeholders (copying in the Tech/Exec as needed) |  |